## 22.4
ID | Prio | Epic | User Story | COS | Effort |  | From ID | Task | Effort
1 |  |  | As a user I want to have a clean website in order to have an overview | easy to use, easy to find ingredients for a product | 20 |  | 1 | create html for website | 5
2 |  |  | As a user I want to scan my products fast in order to know if i eat healthy food or not. | simple and fast scanning process | 4 |  | 1 | create css for website | 2
3 |  |  | As a user I want to scan all products at once in order to save time. | you don´t need to scan all products individually | 25 |  | 1 | create js for website | 8
[7 empty] | 1 | include database with website/program | 5
[7 empty] | 2 | find a big database | 2
[7 empty] | 2 | create database | 2
[7 empty] | 3 | assamble hardware | 2
[7 empty] | 3 | connect cam with software | 5
[7 empty] | 3 | code program for scanning | 13 | inform about how to scan | 9
[7 empty] | 3 | send data to website | 5 | write the code | 4
[8 empty] | Total | 49
[5 empty] | Date | Effort
[5 empty] | 2022-04-22 | 49
2022-04-29
2022-05-06
2022-05-13
2022-05-20
2022-05-27
2022-06-03
2022-06-10
2022-06-17
2022-06-24
2022-07-01
2022-07-08
2022-07-15
2022-07-22
2022-07-29
2022-08-05
2022-08-12
2022-08-19
Update 6.5
ID | Prio | Epic | User Story | COS | Effort |  | From ID | Task | Effort
1 |  |  | As a user I want to have a clean website in order to have an overview | easy to use, easy to find ingredients for a product | 18 |  | 1 | create html for website | 3
2 |  |  | As a user I want to scan my products fast in order to know if i eat healthy food or not. | simple and fast scanning process | 0 |  | 1 | create css for website | 2
3 |  |  | As a user I want to scan all products at once in order to save time. | you don´t need to scan all products individually | 25 |  | 1 | create js for website | 8
[7 empty] | 1 | include database with website/program | 5
[7 empty] | 2 | find a big database | 0
[7 empty] | 2 | create database | 0
[7 empty] | 3 | assamble hardware | 2
[7 empty] | 3 | connect cam with software | 5
[7 empty] | 3 | code program for scanning | 13 | inform about how to scan | 9
[7 empty] | 3 | send data to website | 5 | write the code | 4
[8 empty] | Total | 43
[5 empty] | Date | Effort
[5 empty] | 2022-04-22 | 49
[5 empty] | 2022-04-29 | 46
[5 empty] | 2022-05-06 | 43
2022-05-13
2022-05-20
2022-05-27
2022-06-03
2022-06-10
2022-06-17
2022-06-24
2022-07-01
2022-07-08
2022-07-15
2022-07-22
2022-07-29
2022-08-05
2022-08-12
2022-08-19

## 29.4
ID | Prio | Epic | User Story | COS | Effort |  | From ID | Task | Effort
1 |  |  | As a user I want to have a clean website in order to have an overview | easy to use, easy to find ingredients for a product | 20 |  | 1 | create html for website | 5
2 |  |  | As a user I want to scan my products fast in order to know if i eat healthy food or not. | simple and fast scanning process | 1 |  | 1 | create css for website | 2
3 |  |  | As a user I want to scan all products at once in order to save time. | you don´t need to scan all products individually | 25 |  | 1 | create js for website | 8
[7 empty] | 1 | include database with website/program | 5
[7 empty] | 2 | find a big database | 0
[7 empty] | 2 | create database | 1
[7 empty] | 3 | assamble hardware | 2
[7 empty] | 3 | connect cam with software | 5
[7 empty] | 3 | code program for scanning | 13 | inform about how to scan | 9
[7 empty] | 3 | send data to website | 5 | write the code | 4
[8 empty] | Total | 46
[5 empty] | Date | Effort
[5 empty] | 2022-04-22 | 49
[5 empty] | 2022-04-29 | 46
2022-05-06
2022-05-13
2022-05-20
2022-05-27
2022-06-03
2022-06-10
2022-06-17
2022-06-24
2022-07-01
2022-07-08
2022-07-15
2022-07-22
2022-07-29
2022-08-05
2022-08-12
2022-08-19

## 6.5
ID | Prio | Epic | User Story | COS | Effort |  | From ID | Task | Effort
1 |  |  | As a user I want to have a clean website in order to have an overview | easy to use, easy to find ingredients for a product | 18 |  | 1 | create html for website | 3
2 |  |  | As a user I want to scan my products fast in order to know if i eat healthy food or not. | simple and fast scanning process | 0 |  | 1 | create css for website | 2
3 |  |  | As a user I want to scan all products at once in order to save time. | you don´t need to scan all products individually | 25 |  | 1 | create js for website | 8
[7 empty] | 1 | include database with website/program | 5
[7 empty] | 2 | find a big database | 0
[7 empty] | 2 | create database | 0
[7 empty] | 3 | assamble hardware | 2
[7 empty] | 3 | connect cam with software | 5
[7 empty] | 3 | code program for scanning | 13 | inform about how to scan | 9
[7 empty] | 3 | send data to website | 5 | write the code | 4
[8 empty] | Total | 43
[5 empty] | Date | Effort
[5 empty] | 2022-04-22 | 49
[5 empty] | 2022-04-29 | 46
[5 empty] | 2022-05-06 | 43
2022-05-13
2022-05-20
2022-05-27
2022-06-03
2022-06-10
2022-06-17
2022-06-24
2022-07-01
2022-07-08
2022-07-15
2022-07-22
2022-07-29
2022-08-05
2022-08-12
2022-08-19

## 13.5
COS | Effort |  | From ID | Task | Effort
easy to use, easy to find ingredients for a product | 18 |  | 1 | create html for website | 3
simple and fast scanning process | 0 |  | 1 | create css for website | 2
you don´t need to scan all products individually | 19 |  | 1 | create js for website | 8
|  |  | 1 | include database with website/program | 5
|  |  | 2 | find a big database | 0
|  |  | 2 | create database | 0
|  |  | 3 | assamble hardware | 0
|  |  | 3 | connect cam with software | 5
|  |  | 3 | code program for scanning | 9 | inform about how to scan | 5
|  |  | 3 | send data to website | 5 | write the code | 4
|  |  |  | Total | 37
| Date | Effort
| 2022-04-22 | 49
| 2022-04-29 | 46
| 2022-05-06 | 43
| 2022-05-13 | 37
2022-05-20
2022-05-27
2022-06-03
2022-06-10
2022-06-17
2022-06-24
2022-07-01
2022-07-08
2022-07-15
2022-07-22
2022-07-29
2022-08-05
2022-08-12
2022-08-19

## 20.5
Epic | User Story | COS | Effort |  | From ID | Task | Effort
| As a user I want to have a clean website in order to have an overview | easy to use, easy to find ingredients for a product | 17 |  | 1 | create html for website | 3
| As a user I want to scan my products fast in order to know if i eat healthy food or not. | simple and fast scanning process | 0 |  | 1 | create css for website | 2
| As a user I want to scan all products at once in order to save time. | you don´t need to scan all products individually | 13 |  | 1 | create js for website | 7
[5 empty] | 1 | include database with website/program | 5
[5 empty] | 2 | find a big database | 0
[5 empty] | 2 | create database | 0
[5 empty] | 3 | assamble hardware | 0
[5 empty] | 3 | connect cam with software | 0
[5 empty] | 3 | code program for scanning | 8 | inform about how to scan | 4
[5 empty] | 3 | send data to website | 5 | write the code | 4
[6 empty] | Total | 30
|  |  | Date | Effort
|  |  | 2022-04-22 | 49
|  |  | 2022-04-29 | 46
|  |  | 2022-05-06 | 43
|  |  | 2022-05-13 | 37
|  |  | 2022-05-20 | 30
2022-05-27
2022-06-03
2022-06-10
2022-06-17
2022-06-24
2022-07-01
2022-07-08
2022-07-15
2022-07-22
2022-07-29
2022-08-05
2022-08-12
2022-08-19

## 10.6
Epic | User Story | COS | Effort |  | From ID | Task | Effort
| As a user I want to have a clean website in order to have an overview | easy to use, easy to find ingredients for a product | 12 |  | 1 | create html for website | 0
| As a user I want to scan my products fast in order to know if i eat healthy food or not. | simple and fast scanning process | 0 |  | 1 | create css for website | 0
| As a user I want to scan all products at once in order to save time. | you don´t need to scan all products individually | 13 |  | 1 | create js for website | 7
[5 empty] | 1 | include database with website/program | 5
[5 empty] | 2 | find a big database | 0
[5 empty] | 2 | create database | 0
[5 empty] | 3 | assamble hardware | 0
[5 empty] | 3 | connect cam with software | 0
[5 empty] | 3 | code program for scanning | 8 | inform about how to scan | 4
[5 empty] | 3 | send data to website | 5 | write the code | 4
[6 empty] | Total | 25
|  |  | Date | Effort
|  |  | 2022-04-22 | 49
|  |  | 2022-04-29 | 46
|  |  | 2022-05-06 | 43
|  |  | 2022-05-13 | 37
|  |  | 2022-05-20 | 30
|  |  | 2022-05-27 | 30
|  |  | 2022-06-03 | 30
|  |  | 2022-06-10 | 25
2022-06-17
2022-06-24
2022-07-01
2022-07-08
2022-07-15
2022-07-22
2022-07-29
2022-08-05
2022-08-12
2022-08-19

## 17.6
User Story | COS | Effort |  | From ID | Task | Effort
As a user I want to have a clean website in order to have an overview | easy to use, easy to find ingredients for a product | 12 |  | 1 | create html for website | 0
As a user I want to scan my products fast in order to know if i eat healthy food or not. | simple and fast scanning process | 0 |  | 1 | create css for website | 0
As a user I want to scan all products at once in order to save time. | you don´t need to scan all products individually | 9 |  | 1 | create js for website | 7
|  |  |  | 1 | include database with website/program | 5
|  |  |  | 2 | find a big database | 0
|  |  |  | 2 | create database | 0
|  |  |  | 3 | assamble hardware | 0
|  |  |  | 3 | connect cam with software | 0
|  |  |  | 3 | code program for scanning | 4 | inform about how to scan | 0
|  |  |  | 3 | send data to website | 5 | write the code | 4
[5 empty] | Total | 21
|  | Date | Effort
|  | 2022-04-22 | 49
|  | 2022-04-29 | 46
|  | 2022-05-06 | 43
|  | 2022-05-13 | 37
|  | 2022-05-20 | 30
|  | 2022-05-27 | 30
|  | 2022-06-03 | 30
|  | 2022-06-10 | 25
|  | 2022-06-17 | 21
2022-06-24
2022-07-01
2022-07-08
2022-07-15
2022-07-22
2022-07-29
2022-08-05
2022-08-12
2022-08-19

## 24.6
User Story | COS | Effort |  | From ID | Task | Effort
As a user I want to have a clean website in order to have an overview | easy to use, easy to find ingredients for a product | 5 |  | 1 | create html for website | 0
As a user I want to scan my products fast in order to know if i eat healthy food or not. | simple and fast scanning process | 0 |  | 1 | create css for website | 0
As a user I want to scan all products at once in order to save time. | you don´t need to scan all products individually | 5 |  | 1 | create js for website | 0
|  |  |  | 1 | include database with website/program | 5
|  |  |  | 2 | find a big database | 0
|  |  |  | 2 | create database | 0
|  |  |  | 3 | assamble hardware | 0
|  |  |  | 3 | connect cam with software | 0
|  |  |  | 3 | code program for scanning | 0 | inform about how to scan | 0
|  |  |  | 3 | send data to website | 5 | write the code | 0
[5 empty] | Total | 10
|  | Date | Effort
|  | 2022-04-22 | 49
|  | 2022-04-29 | 46
|  | 2022-05-06 | 43
|  | 2022-05-13 | 37
|  | 2022-05-20 | 30
|  | 2022-05-27 | 30
|  | 2022-06-03 | 30
|  | 2022-06-10 | 25
|  | 2022-06-17 | 25
|  | 2022-06-24 | 10
2022-07-01
2022-07-08
2022-07-15
2022-07-22
2022-07-29
2022-08-05
2022-08-12
2022-08-19