## Tabelle1
Simple Planning and Monitoring Sheet
Task | Orig. Est. | Curr.Est. | Effort | Remain | Responsible
Hardware
buy hardware | 4
assemble hardware | 6
Database
find database | 8 | 16 | 15 | 1
sql coding | 10 | 16 | 6 | 10
Scanning
inform about scanning | 3 | 6 | 6 | 0
code scanning program | 12
send scan to aws | 20
Website
create basic design for website | 3 | 3 | 3 | 0
finish front-end | 12
finish back-end | 15
Hosting
Hosting database and website | 12 | 12 | 3 | 9
Total | 105