## Tabelle1
ID | Prio | Epic | User Story | COS | Effort |  | From ID | Task | Effort
1 |  |  | As a user I want to have a clean website in order to have an overview | easy to use, easy to find ingredients for a product | 20 |  | 1 | create html for website | 5
2 |  |  | As a user I want to scan my products fast in order to know if i eat healthy food or not. | simple and fast scanning process | 4 |  | 1 | create css for website | 2
3 |  |  | As a user I want to scan all products at once in order to save time. | you don´t need to scan all products individually | 25 |  | 1 | create js for website | 8
[7 empty] | 1 | include database with website/program | 5
[7 empty] | 2 | find a big database | 2
[7 empty] | 2 | create database | 2
[7 empty] | 3 | assamble hardware | 2
[7 empty] | 3 | connect cam with software | 5
[7 empty] | 3 | code program for scanning | 13 | inform about how to scan | 9
[7 empty] | 3 | send data to website | 5 | write the code | 4
[8 empty] | Total | 49
Update 29.4
|  |  |  | COS | Effort |  | From ID | Task | Effort
|  |  |  | easy to use, easy to find ingredients for a product | 20 |  | 1 | create html for website | 5
|  |  |  | simple and fast scanning process | 1 |  | 1 | create css for website | 2
|  |  |  | you don´t need to scan all products individually | 25 |  | 1 | create js for website | 8
[7 empty] | 1 | include database with website/program | 5
[7 empty] | 2 | find a big database | 0
[7 empty] | 2 | create database | 1
[7 empty] | 3 | assamble hardware | 2
[7 empty] | 3 | connect cam with software | 5
[7 empty] | 3 | code program for scanning | 13 | inform about how to scan | 9
[7 empty] | 3 | send data to website | 5 | write the code | 4
[8 empty] | Total | 46
[5 empty] | Date | Effort
[5 empty] | 2022-04-22 | 49
[5 empty] | 2022-04-29 | 46
[5 empty] | 2022-05-06 | 43
2022-05-13
2022-05-20
2022-05-27
2022-06-03
2022-06-10
2022-06-17
2022-06-24
2022-07-01
2022-07-08
2022-07-15
2022-07-22
2022-07-29
2022-08-05
2022-08-12
2022-08-19
Update 6.5
|  |  |  | COS | Effort |  | From ID | Task | Effort
|  |  |  | easy to use, easy to find ingredients for a product | 18 |  | 1 | create html for website | 3
|  |  |  | simple and fast scanning process | 0 |  | 1 | create css for website | 2
|  |  |  | you don´t need to scan all products individually | 25 |  | 1 | create js for website | 8
[7 empty] | 1 | include database with website/program | 5
[7 empty] | 2 | find a big database | 0
[7 empty] | 2 | create database | 0
[7 empty] | 3 | assamble hardware | 2
[7 empty] | 3 | connect cam with software | 5
[7 empty] | 3 | code program for scanning | 13 | inform about how to scan | 9
[7 empty] | 3 | send data to website | 5 | write the code | 4
[8 empty] | Total | 43
[5 empty] | Date | Effort
[5 empty] | 2022-04-22 | 49
[5 empty] | 2022-04-29 | 46
[5 empty] | 2022-05-06 | 43
2022-05-13
2022-05-20
2022-05-27
2022-06-03
2022-06-10
2022-06-17
2022-06-24
2022-07-01
2022-07-08
2022-07-15
2022-07-22
2022-07-29
2022-08-05
2022-08-12
2022-08-19